## Cover
Effort Calculation
Total Cost | 15565.8465
Man Hours | 56.5
Man Days | 7.0625

## Summery
Personel |  |  | Project
Name | Man Hr | Cost | Name | Man Hr | Cost
Arpan Kar | 39.5 | 12458.585 | Business | 6.5 | 2959.265
Brij Mohan Sharma | 8 | 1657.204 | School | 32.5 | 5800.1975
Hassan Shaw | 0 | 0 | Service | 10 | 2722.55
Kanti Ranjan Mondal | 0 | 0 | Retail | 4 | 2012.324
Rakhi Dey Kar | 0 | 0 | Tourism | 3.5 | 2071.51
Sourav Saha | 0 | 0 | Total | 56.5 | 15565.8465
Sudarshan Acharya | 9 | 1450.0575
Total | 56.5 | 15565.8465

## Business
Date | By | Type | Hour | Skill Index | Member Index | Unit Cost | Weitage | Cost | Comment
19.10.2015 | Arpan Kar | HR Strategy | 5 | 4 | 1 | 355.11 | 1 | 1775.55 | Preparing Effort sheet, and other templates
23.10.2015 | Arpan Kar | Business Strategy | 0.5 | 1 | 1 | 1183.71 | 1 | 591.855 | Discussion on path and review
26.10.2015 | Arpan Kar | Architecture | 1 | 10 | 1 | 591.86 | 1 | 591.86 | Technical Template creation
|  |  |  | 0 | 0 | 355.11 | 0.5 | 0
|  |  |  | 0 | 0 | 355.11 | 0 | 0

## School
Date | By | Type | Hour | Skill Index | Member Index | Unit Cost | Weitage | Cost | Comment
21.10.2015 | Sudarshan Acharya | Operation Management | 2 | 7 | 7 | 591.86 | 0.5 | 591.86
22.10.2015 | Sudarshan Acharya | Operation Management | 2 | 7 | 7 | 591.86 | 0.5 | 591.86
24.10.2015 | Sudarshan Acharya | Business Analysis | 2 | 9 | 7 | 177.56 | 0.5 | 177.56
26.10.2015 | Arpan Kar | Architecture | 1 | 10 | 1 | 591.86 | 1 | 591.86 | Discussion on how to progress with requirement, Changing model
27.10.2015 | Arpan Kar | Business Analysis | 1 | 9 | 1 | 177.56 | 1 | 177.56 | Adding requirement using use case and class diagram
28.10.2015 | Arpan Kar | Business Analysis | 1 | 9 | 1 | 177.56 | 1 | 177.56 | Making model iterative
30.10.2015 | Arpan Kar | Architecture | 2 | 10 | 1 | 591.86 | 1 | 1183.72 | Forming solution structure
30.10.2015 | Arpan Kar | Coding | 4 | 12 | 1 | 118.37 | 1 | 473.48 | Coding for basic framework
31.10.2015 | Arpan Kar | Coding | 6 | 12 | 1 | 118.37 | 1 | 710.22 | Coding for basic framework and implementation of Student sample
04.11.2015 | Arpan Kar | Business Analysis | 0.5 | 9 | 1 | 177.56 | 1 | 88.78 | Modeling student
04.11.2015 | Arpan Kar | Coding | 4 | 12 | 1 | 118.37 | 1 | 473.48 | Developed basic framework and studen as test form
05.11.2015 | Arpan Kar | Coding | 4 | 12 | 1 | 118.37 | 1 | 473.48 | Restructuring UI using control. Training for Sample code.
05.11.2015 | Sudarshan Acharya | Coding | 2 | 12 | 7 | 118.37 | 0.25 | 59.185 | Added Religion component
06.11.2015 | Sudarshan Acharya | Coding | 1 | 12 | 7 | 118.37 | 0.25 | 29.5925 | Added Gender component
|  |  |  | 0 | 0 | 118.37 | 0 | 0
|  |  |  | 0 | 0 | 177.56 | 0 | 0
|  |  |  | 0 | 0 | 118.37 | 0 | 0
|  |  |  | 0 | 0 | 591.86 | 0 | 0

## Service
Date | By | Type | Hour | Skill Index | Member Index | Unit Cost | Weitage | Cost | Comment
| Hassan Shaw | Project Management |  | 8 | 3 | 236.74 | 0 | 0
| Hassan Shaw | Project Management |  | 8 | 3 | 236.74 | 0 | 0
22.10.2015 | Arpan Kar | Architecture | 4 | 10 | 1 | 591.86 | 1 | 2367.44 | Discussion on risk of the migration project Ascent, Technical discussion of feasibility
22.10.2015 | Brij Mohan Sharma | Project Management | 4 | 8 | 2 | 236.74 | 0.2 | 189.392 | Discussion of project
24.10.2015 | Arpan Kar | Project Management | 1 | 8 | 1 | 236.74 | 0.5 | 118.37 | Discussion on Ascent project.
24.10.2015 | Brij Mohan Sharma | Project Management | 1 | 8 | 2 | 236.74 | 0.2 | 47.348 | Discussion of project

## Retail
Date | By | Type | Hour | Skill Index | Member Index | Unit Cost | Weitage | Cost | Comment
22.10.2015 | Brij Mohan Sharma | Operation Management | 1 | 7 | 2 | 591.86 | 0.8 | 473.488 | Discussion on business model
22.10.2015 | Arpan Kar | Operation Management | 1 | 7 | 1 | 591.86 | 1 | 591.86 | Discussion on business model
22.10.2015 | Brij Mohan Sharma | Operation Management | 2 | 7 | 2 | 591.86 | 0.8 | 946.976 | Preparation of Business model
|  |  |  | 0 | 0 | 355.11 | 0.5 | 0
|  |  |  | 0 | 0 | 355.11 | 0 | 0

## Tourism
Date | By | Type | Hour | Skill Index | Member Index | Unit Cost | Weitage | Cost | Comment
23.10.2016 | Arpan Kar | Operation Management | 3 | 7 | 1 | 591.86 | 1 | 1775.58 | Updating business model to target April 2016 launch
27.10.2016 | Arpan Kar | Operation Management | 0.5 | 7 | 1 | 591.86 | 1 | 295.93 | Calculating sales commision, and how it will fit
|  |  |  | 0 | 0 | 946.97 | 1 | 0
|  |  |  | 0 | 0 | 355.11 | 0.5 | 0
|  |  |  | 0 | 0 | 355.11 | 0 | 0

## Team Member
Till March 2016 |  | Competency Metrix
|  | Strategy | [5 empty] | Development | [8 empty] | HR & Administration | [9 empty] | Marketing & Sales |  |  |  | Finance
Sr | Name | Business Strategy | Offering Strategy | Finance Strategy | HR Strategy | Administration Strategy | Marketing Strategy | Operation Management | Project Management | Business Analysis | Architecture | Design | Coding | Testing | Usability Design | Visual Design | HR Management | HR Execution | Resourcing | Training | Office management | Office Execution | Infrustructure Management | Infrustructure Execution | Travel Execution | Customer Relationship Management | Marketing | Market Survey | Sale Management | End Sale | Accounting | Payroll | Taxation | Audit
1 | Arpan Kar | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 0.8 | 1 | 0.8 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
2 | Brij Mohan Sharma | 0.5 | 0.2 | 0 | 0.01 | 0.01 | 0.5 | 0.8 | 0.2 | 0.5 | 0.3 | 1 | 1 | 0.5 | 0.8 | 0.5 | 0 | 0 | 0.2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Hassan Shaw
4 | Kanti Ranjan Mondal
5 | Rakhi Dey Kar
6 | Sourav Saha
7 | Sudarshan Acharya | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0.25 | 0.5 | 0 | 0 | 0.25 | 0.25 | 0.5 | 0 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25 | 1 | 0.25 | 0.25 | 0.25 | 0.5 | 0.25 | 0.8 | 0 | 0

## Skill Set
Category | Sr | Skill | Cost Per Anum! | Cost Per Anum | Cost Per Month | Cost Per Hour
Strategy | 1 | Business Strategy | 10000000 | 2500000 | 208333.3333 | 1183.71
| 2 | Offering Strategy | 8000000 | 2000000 | 166666.6667 | 946.97
| 3 | Finance Strategy | 8000000 | 2000000 | 166666.6667 | 946.97
| 4 | HR Strategy | 3000000 | 750000 | 62500 | 355.11
| 5 | Administration Strategy | 3000000 | 750000 | 62500 | 355.11
| 6 | Marketing Strategy | 8000000 | 2000000 | 166666.6667 | 946.97
Development | 7 | Operation Management | 5000000 | 1250000 | 104166.6667 | 591.86
| 8 | Project Management | 2000000 | 500000 | 41666.6667 | 236.74
| 9 | Business Analysis | 1500000 | 375000 | 31250 | 177.56
| 10 | Architecture | 5000000 | 1250000 | 104166.6667 | 591.86
| 11 | Design | 1500000 | 375000 | 31250 | 177.56
| 12 | Coding | 1000000 | 250000 | 20833.3333 | 118.37
| 13 | Testing | 1000000 | 250000 | 20833.3333 | 118.37
| 14 | Usability Design | 2500000 | 625000 | 52083.3333 | 295.93
| 15 | Visual Design | 1000000 | 250000 | 20833.3333 | 118.37
HR & Admin | 16 | HR Management | 1500000 | 375000 | 31250 | 177.56
| 17 | HR Execution | 600000 | 150000 | 12500 | 71.02
| 18 | Resourcing | 300000 | 75000 | 6250 | 35.51
| 19 | Training | 2000000 | 500000 | 41666.6667 | 236.74
| 20 | Office management | 600000 | 150000 | 12500 | 71.02
| 21 | Office Execution | 300000 | 75000 | 6250 | 35.51
| 22 | Infrustructure Management | 600000 | 150000 | 12500 | 71.02
| 23 | Infrustructure Execution | 300000 | 75000 | 6250 | 35.51
| 24 | Travel Execution | 300000 | 75000 | 6250 | 35.51
| 25 | Customer Relationship Management | 600000 | 150000 | 12500 | 71.02
Sales & Marketing | 26 | Marketing | 2500000 | 625000 | 52083.3333 | 295.93
| 27 | Market Survey | 600000 | 150000 | 12500 | 71.02
| 28 | Sale Management | 1500000 | 375000 | 31250 | 177.56
| 29 | End Sale | 600000 | 150000 | 12500 | 71.02
Finance | 30 | Accounting | 300000 | 75000 | 6250 | 35.51
| 31 | Payroll | 300000 | 75000 | 6250 | 35.51
| 32 | Taxation | 600000 | 150000 | 12500 | 71.02
| 33 | Audit | 1000000 | 250000 | 20833.3333 | 118.37